## ROAD PROJECT data
[21 empty] | Benefits |  | BCR
URL link to POPE report | Project name | Number of years after opening | Forecast year | completion year | Prices base year | forecast cost (£m) | outturn cost (£m) | notes | cost overrun (%) | Explination of cost overrun / underrun | Optimism uplift | preferred route announcement | Public enquiry | Secretary of State decision | Made Orders published | Scheme study comissioned | Scheme study submitted | construction start | opening | duration | forecast (£m) | Outturn (£m) | Forecast | Outturn
https://nationalhighways.co.uk/media/vnvbiop3/a1-coalhouse-to-metro-centre-1ya-pope-report.pdf | A1 Coal House to Metro Centre improvements | 1 | [5 empty] | no cost data | [9 empty] | 2014-09-01 | 2016-09-01 | 24
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130753mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE%20LNMS%20_%20A1%20_%20A69%20Denton%20Interchange%20Signalisation%20Report%20_%20Final.pdf | A1 Denton Interchange | LNMS Evaluation Report | 2009 | 2011 | 1994 | 0.932 | 0.971 | discounted | 4.185% | [6 empty] | 2007-09-01 | 2008-06-01 | 2010-10-18 | 2011-02-11 | 4 | 71.9 | 12.863 | 60.1 | 11
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636087/Full_report.pdf | A1 Dishforth to Leeming | 1 | 2009 | 2012 | 2002 | 286.1 | 251.7 | investment cost, undiscounted. 7YA report only presents PVC | -12.02% | none | ? | [6 empty] | 2009-02-01 | 2012-03-01 | 37 | 317.8 | 283.2 | 1.4 | 0.9
https://nationalhighways.co.uk/media/swajigpw/a1-dishforth-to-leeming-seven-year-after-and-a1-leeming-to-barton-one-year-after-pope-report.pdf | A1 Durham climbing lanes
https://nationalhighways.co.uk/media/swajigpw/a1-dishforth-to-leeming-seven-year-after-and-a1-leeming-to-barton-one-year-after-pope-report.pdf | A1 Peterborough – Blyth Grade Separated Junctions
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130905mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A1%28M%29_Durham_Climbing_Lanes_%28Bradbury_to_Bowburn%29_Report___Final.pdf | A1 Durham climbing lanes - LNMS report | LNMS Evaluation Report | 2004 | 2004 | 2002 | 2.39 | 2.444 | scheme capital cost, undiscounted | 2.259% | [8 empty] | 2004-04-01 | 2004-11-01 | 7 | 6.587 | 7.111 | 8.83 | 34.19
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636090/Full_report.pdf | A1 Peterborough – Blyth Grade Separated Junctions Five Years After Study | 5 |  | 2009 | 2002 | 73 | 82.1 | investment cost, undiscounted | 12.47% | higher construction costs, high land purchase costs and additional maintenance costs |  | 2003-03-01 | 2005-09-01 | 2006-01-01 | 2006-06-01 |  |  | 2006-09-01 | 2009-10-01 | 37 | 1061 | 407.8 | 16 | 4.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603131021mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A1_Rainton_Crossroads_Report___Final.pdf | A1 Rainton Crossroads | LNMS Evaluation Report |  | 2004 | 2002 | 1.693 | 1.974 | scheme cost, discounted | 16.6% | [8 empty] | 2003-09-01 | 2004-08-01 | 11 | 2.374 | 3.445 | 1.4 | 1.75
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124256/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A1-Stannington-Junction/POPE%20_%20A1%20Stannington%20FYA%20_%20final.pdf | A1 Stannington Grade Separated Junction | 5 | 2003 | 2004 | 2002 | 5.4 | 6.9 | investment cost, undiscounted | 27.78% | none | [7 empty] | 2003-06-01 | 2004-10-01 | 16 | 48.4 | 36.5 | 7.9 | 4.6
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A1-Willowburn-Denwick-Improvement/POPE%20_%20A1%20Willowburn%20to%20Denwick%20FYA%20report%20_%20final.pdf | A1 Willowburn to Denwick Improvements | 5 |  | 2003 | 1998 | 7.3 | 8.3 | investment cost, undiscounted | 13.7% | [8 empty] | 2001-03-01 | 2003-03-01 | 24 | 17 | 4.4 | 4.1 | 0.5
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636109/Full_report.pdf | A1(M) Bramham to Wetherby | 5 | 2007 | 2009 | 2002 | 56.2 | 61 | investment cost, undiscounted | 8.541% |  |  | 2003-10-01 | 2006-02-01 | 2007-04-01 |  |  |  | 2007-04-01 | 2009-07-01 | 27 | 279.4 | 65 | 4.6 | 1.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123301mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A1M-Ferrybridge-Hook-Moor/POPE_A1M_Ferrybridge_FYA_FINAL.pdf | A1(M) Ferrybridge to Hook Moor Improvement |  | 2001 | 2006 | 2002 | 194.2 | 183.6 | investment cost, undiscounted | -5.458% | [8 empty] | 2003-05-01 | 2006-01-01 | 32 | 910.2 | 591.8 | 5 | 3.5
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A1M-Wetherby-Walshford/A1%28M%29%20Wetherby%20to%20Walshford%20POPE%20FYA%20-%20website%20version.pdf | A1(M) Wetherby – Walshford | 5 | 2001 | 2005 | 2002 | 55.3 | 83.5 | investment cost, undiscounted | 50.99% | "- the layout of the scheme as built as different from that in the appraisal with the closure of a junction and addition of an extra link road. - Price conversions here have been made using the RPI. It is known that inflation for construction costs and land values outstripped general inflation during the period here, so much of the overspend can be assigned to this. - VAT is not included in the forecast, but outturn costs for this scheme which was constructed on land outside the highway boundary will include an amount of nonrecoverable VAT. | [7 empty] | 2003-05-01 | 2005-08-01 | 27 | 147.1 | 242.3 | 2.8 | 3.2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130925mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE%20LNMS%20_%20A1%28M%29%20_%20M18%20Wadworth%20Interchange%20Signalisation%20Report%20_%20Final.pdf | A1(M)/M18 Wadworth Interchange | LNMS Evaluation Report | 2010 | 2011 | 2002 | 1.7938 | 1.566 | construction cost, includes 10% optimism bias | -12.7% | "without optimism bias, the scheme costs would be more accurately estimated" | 10% |  |  |  |  | 2009-01-01 | 2010-10-01 | 2010-12-06 | 2011-03-31 | 3 | 94.614 | 20.18 | 52.7 | 12.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A10-Wadesmill-to-Colliers-End-Bypass/POPE%20_%20A10%20Wadesmill%20FYA%20_%20website%20part%20B.pdf | A10 Wadesmill, High Cross and Colliers End Bypass | 5 |  | 2004 | 2002 | 23.7 | 40.8 |  | 72.15% | [9 empty] | 2004-10-08 |  | 106.6 | 121.1 | 4.5 | 3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A1033%20Hedon%20Road%20Improvement/POPE%20_%20A1033%20Hedon%20Rd%20FYA%20_%20final.pdf | A1033 Hedon Road Improvement | 5 |  | 2003 | 2002 | 59.5 | 86.7 | scheme cost, undiscounted | 45.71% | none | [7 empty] | 2001-06-01 | 2003-11-01 | 29 | 260 | 172 | 4.3 | 1.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A11-Attleborough-Bypass/pope-a11-attleborough-bypass-fya-final.pdf | A11 Attleborough Bypass Improvements |  | 2004 | 2007 | 2002 | 19.8 | 27.5 | investment cost, undiscounted | 38.89% | due to higher investment costs [Works, Prep & Supervision + Lands] combined with smaller indirect tax benefits | [7 empty] | 2005-08-01 | 2007-02-01 | 17 | 71.9 | 54.9 | 6.3 | 2.7
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782590/POPE_A11_Fiveways_to_Thetford_OYA_Report.pdf | A11 Fiveways to Thetford | 1 | 2012 | 2014 | 2002 | 83.9 | 80.2 | investment cost, undiscounted | -4.41% | [8 empty] | 2013-01-01 | 2014-12-01 | 23 | 1235.7 | 1156.6 | 15.9 | 15.2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A11-Roudham-Heath-Attleborough-Improvement/A11%20Roudham%20to%20Attleborough%20POPE%20FYA%20-%20Website%20version.pdf | A11 Roudham Heath to Attleborough Improvements |  | 2001 | 2003 | 1988 | 16.9 | 31.1 | investment cost, undiscounted | 84.02% | Fees for renewals spent at same time | [7 empty] | 2001-05-01 | 2003-03-01 | 22 |  |  | 1.4 | 4.2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130822mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/A12%20Hatfield%20Peverel%20%28Junctions%2020b%20to%2021%29.pdf | A12 Hatfield Peverel POPE of LNMS | LNMS Evaluation Report |  | 2010 | 2002 | 3.189 | 2.026 | Present Value of Costs, discounted | -36.47% | - Works costs around £0.5m less than anticipated; - Preparation costs were around £240,000 more than anticipated; and - Predicted cost includes risk allowance and optimism bias (around £360,000) | 12.73% |  |  |  |  | 1905-06-28 | 1905-06-29 | 2009-11-03 | 2010-04-20 | 5 | 31.452 | 51.042 | 7.7 | 15.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130633mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A12_Stanway_to_Spring_Lane_Interchange_Report___Final.pdf | A12 Stanway to Spring Lane Interchange |  |  | 2006 | 2002 | 2.102 | 2.32 | total project costs, undiscounted | 10.37% | [8 empty] | 2001-02-01 | 2006-01-01 | 59 | 7.224 | 11.685 | 3.3 | 4.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A120%20Stansted%20to%20Braintree%20Improvement/POPE%20_%20A120%20Stansted%20to%20Braintree%20FYA%20_%20website%20part%20B.pdf | A120 Stansted to Braintree |  | 1988 | 2004 | 2002 | 139.15 | 100.17 | investment cost, undiscounted | -28.01% | none | ? | 2001-03-01 | 1996-04-01 |  | 2001-07-01 |  |  | 2001-09-01 | 2004-07-09 | 34 | 646.4 | 1215.8 | 4.09 | 12.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130200mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A14_Brampton_Hut_Interchange_Report___Final.pdf | A14 Brampton Hut Interchange – New Traffic Signals |  |  | 2006 | 2002 | 2.024 | 1.912 | total project costs, undiscounted | -5.534% | [8 empty] | 2005-03-01 | 2006-12-01 | 21 | 12.138 | 11.296 | 5.32 | 5.63
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130501mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE%20LNMS%20_%20A14%20Fen%20Ditton%20to%20Girton%20Safety%20Cameras%20Report%20_%20Final.pdf | A14 Girton to Fen Ditton Safety Cameras | LNMS Evaluation Report |  | 2011 | 2002 | 1.5165 | 0.93257 | construction cost, discounted | -38.51% | "partly due to the risk allowance and optimism bias included in the predicted costs (around £140,000)" | 3% | [6 empty] | 2010-12-01 | 2011-03-21 | 3 | 15.116 | 11.435 | 7.3 | 8.1
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/448771/A14_Haughley_FYA_report_Final__compressed_.pdf | A14 Haughley New Street to Stowmarket Improvement | 5 | 2006 | 2008 | 2002 | 25 | 30.3 | scheme cost, undiscounted | 21.2% | none |  | 2004-03-01 | 2006-11-01 | 2007-04-01 |  |  |  | 2007-06-01 | 2008-12-01 | 18 | 91.7 | 74.4 | 4.4 | 2.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130538mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A14_Huntingdon_to_Cambridge_Safety_Cameras_Report___Final.pdf | A14 Huntingdon to Cambridge Safety Cameras |  |  | 2007 | 2002 | 2.499 | 2.802 | total project costs, undiscounted | 12.12% | [8 empty] | 2007-01-01 | 2007-07-01 | 6 | 1.525 | 9.634 | 0.49 | 3.4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130716mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A14_Jane_Coston_Bridge_Report___Final.pdf | A14 Jane Coston Bridge |  |  | 2004 | 1994 | 1.212 | 1.3889 | Scheme Present Value of Cost (PVC), discounted | 14.59% | [9 empty] | 2004-05-01 |  | 3.8562 | 2.3527 | 3.18 | 1.82
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782632/POPE_A14_Kettering_Bypass_OYA_Report.pdf | A14 Junctions 7-9 Kettering Bypass Improvement | 1 |  | 2015 | 2010 | 39.238 | 36.666 | investment cost, undiscounted | -6.555% | none | ? | [6 empty] | 2013-11-11 | 2015-05-01 | 18 | 228.2 | 170.1 | 5.6 | 4.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A14-Rookery-Crossroads-GSJ/A14%20Rookery%20GSJ%20POPE%20OYA%20-%20website%20version.pdf | A14 Rookery Crossroads |  | 2002 | 2006 | 1998 | 10.18 | 14.32 | investment cost, undiscounted | 40.67% | [8 empty] | 2004-08-01 | 2006-03-01 | 19
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130316mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A14_Spittals_Interchange_Report___Final.pdf | A14 Spittals Interchange – Provision of Traffic Signals |  |  | 2006 | 2002 | 1.9277 | 1.9624 | Present Value of Costs, discounted | 1.799% | [8 empty] | 2005-10-01 | 2006-01-01 | 3 | 3.607 | 3.907 | 2.07 | 1.99
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130258mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A19_Black_Swan_Bridge_Report___Final.pdf | A19 Black Swan Bridge |  |  | 2008 | 2002 | 1.736 | 1.965 | Total PVC | 13.19% | [9 empty] | 2008-11-01 |  | 6.669 | 9.521 | 4.4 | 4.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A2-Bean-Cobham-Phase-1-Bean-Pepperhill/A2%20Bean%20to%20Cobham%20Phase%201%20%28FYA%29%20and%20Phase%202%20%28OYA%29%20-%20website%20version.pdf | A2 Bean – Cobham (Phase 1) | 5 | 2000 | 2004 | 2002 | 17.4 | 22.1 | investment cost, undiscounted | 27.01% | "forecast costs did not include for land take but £3.6m was actually spent. The reason for no original land take being planned has not been identified by POPE. Overall spend was 27% above the forecast, predominantly due to these additional land costs" |  |  |  | 1905-06-23 |  |  |  | 2002-06-01 | 2004-12-01
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636094/Final_report.pdf | A2 Bean – Cobham (Phase 2) | 5 |  | 2009 | 2002 | 115.9 | 113.4 | investment cost, undiscounted | -2.157% |  |  | 1905-06-24 | 1905-06-27 | 1905-06-27 |  |  |  | 2006-06-01 | 2009 |  | 360.4 | 260.6 | 3 | 2.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130252mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A2_Kingston_Bridleway_Bridge_Report___Final.pdf | A2 Kingston Bridleway Bridge | 1 |  | 2010 | 2002 | 1.998 | 1.525 | total project costs, discounted | -23.67% | "The MAC was unable to provide an explanation as to why the scheme was delivered significantly below the cost predicted however they confirmed the scheme was delivered as expected" | ? | [6 empty] | 2009-11-01 | 2010-03-01 | 4 | 3.41 | 0 | 1.8 | 0
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636112/Full_report.pdf | A2/A282 Dartford Improvement | 5 |  | 2007 | 2002 | 94.2 | 106.2 | investment cost, undiscounted | 12.74% | [8 empty] | 2006-08-01 | 2007-12-01 | 16 | 182.7 | 185.8 | 1.8 | 1.6
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130937mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A21_John_s_Cross_Junction_Improvement_Report___Final.pdf | A21 Johns Cross Junction Improvement |  |  | 2003 | 1994 | 1.1735 | 0.88571 | scheme cost, discounted | -24.52% | none | ? | [7 empty] | 2003-05-01 |  | 1.087 | 1.003 | 0.93 | 1.13
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A21-Lamberhurst-Bypass/POPE%20_%20A21%20Lamberhurst%20FYA%20_%20Website%20part%20E.pdf | A21 Lamberhurst Bypass |  |  | 2005 | 2002 | 16.1 | 25 | investment cost, undiscounted | 55.28% | Land costs, including "The original estimate (forecast) under-valued the injurious affection compensation (effect on retained property) to be paid to the National Trust;" (Injurious affection means the effect caused to neighbouring land from a public project). and "One of the main agricultural landowners in the vicinity of the scheme was paid for a severed field becoming uneconomical for hop farming, and as above this was under-estimated in the forecast" | [10 empty] | 51.9 | 56.2 | 3 | 2
https://nationalhighways.co.uk/media/ldzouc4q/a21-tonbridge-to-pembury-1ya-pope-report.pdf | A23 Handcross to Warninglid | 1 | [5 empty] | no cost data | [9 empty] | 2015-04-01 | 2017-09-01 | 29
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782599/POPE_A23_Handcross_to_Warninglid_OYA_Report.pdf | A23 Handcross to Warninglid | 1 | 2012 | 2014 | 2002 | 59.2 | 60.1 | investment cost, undiscounted | 1.52% | [8 empty] | 2012-06-01 | 2014-10-01 | 28 | 213.9 | 79.87 | 5.2 | 1.87
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123049mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A249%20Iwade%20-%20Queenborough%20Improvement%20%28DBFO%29/POPE_A249_Iwade_Queenborough_FYA_FINAL.pdf | A249 Iwade to Queenborough Improvement | 5 | 2006 | 2006 | 2002 | 76.2 | 85.3 | investment cost, undiscounted | 11.94% | [8 empty] | 2004-04-01 | 2006-07-01 | 27 | 266.5 | 191.3 | 3.3 | 2.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A27-Polegate-Bypass/A27%20Polegate%20POPE%20FYA%20-%20website%20version.pdf | A27 Polegate Bypass |  |  | 2002 | 1988 | 15.64 | 19.5 | investment cost, undiscounted | 24.68% | "An outturn cost of £19.5m which is 25% higher than the predicted cost of £15.6m; The primary reason for this increase is due to the increase in land costs which were over £5m higher than predicted [£6.73 rather than £1.1m]. It is likely that this represents national trends in land prices over the period between the planned and actual dates of land purchase" | [7 empty] | 1996-01-01 | 2002-06-01 | 77 | 22.8 | 32.7 | 2.8 | 4.4
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/450897/POPE_A27_Southerham-Beddingham_FYA_final.pdf | A27 Southerham – Beddingham Improvement | 5 | 2006 | 2008 | 2002 | 29.1 | 29.1 | scheme cost, undiscounted | 0% | [8 empty] | 2006-10-01 | 2008-08-01 | 22 | 485.9 | 427.3 | 9.4 | 5.3
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782584/POPE_A3_Hindhead_FYA_Report.pdf | A3 Hindhead | 5 | 2007 | 2011 | 2002 | 322 | 315.6 | investment cost, discounted | -1.988% |  |  | 2001-06-01 | 2005-02-01 |  | 2006-07-01 |  |  | 2007-04-01 | 2011-07-01 | 51 | 727.6 | 773.4 | 2.1 | 2.4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123625mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A30-Bodmin-Indian-Queens-Improvement/POPE___A30_Bodmin-Indian_Queens_FYA___Final.pdf | A30 Bodmin to Indian Queens Improvement | 5 | 2003 | 2007 | 2002 | 70.1 | 77.8 | investment cost, undiscounted | 10.98% | [8 empty] | 2005-07-01 | 2007-07-01 | 24 | 304 | 268.6 | 4.4 | 3.6
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603131002mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A30_Chiverton_Cross_Report___Final.pdf | A30 Chiverton Cross Roundabout Improvement |  |  | 2006 | 2002 | 1.323 | 1.785 | Present value costs, discounted | 34.92% | outturn costs were % above forecasts due to increased spending on construction, preparation and supervision | [7 empty] | 2005-12-01 | 2006-05-01 | 5 | 3.05 | -1.785 | 2.12 | -0.95
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A30A382-Merrymeet-Junction/pope-a30-whiddond-down-fya-final.pdf | A30 Whiddon Down Junction Improvement (formerly Merrymeet roundabout) |  | 2004 | 2006 | 2002 | 7.6 | 10.8 | investment cost, undiscounted | 42.11% | scheme was at an early stage when it entered the TPI (precursor to the Major Schemes Programme) | [7 empty] | 2005-11-01 | 2006-12-01 | 13 | 48.4 | 34.6 | 5.6 | 3.6
https://nationalhighways.co.uk/media/0xhlgnz3/a30-temple-to-higher-carblake-one-year-post-opening-project-evaluation-report.pdf | A34 / M4 J13 Improvement
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A34-ChieveleyM4-Jct-13-Improvement/POPE%20_%20A34%20Chieveley%20FYA%20_%20final.pdf | A34 / M4 J13 Improvement | 5 | 2000 | 2004 | 2002 | 52.6 | 70.6 | investment cost, undiscounted | 34.22% | none | [7 empty] | 2003-05-01 | 2004-08-01 | 15 | 409.7 | 410.7 | 6.4 | 4.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130210mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE%20LNMS%20_%20A35%20Dorchester%20-%20Stinsford%20Roundabout%20Improvements%20Report%20_%20Final.pdf | A35 Stinsford Roundabout |  |  | 2011 | 2002 | 1.5037 | 0.85455 | construction cost, discounted | -43.17% | "there is evidence that the forecast would have been more accurate without the 10% optimism bias included in the predicted costs" | 10% | [6 empty] | 2010-10-01 | 2011-03-31 | 5 | 37.965 | -7.562 | 22.1 | -7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130832mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE%20LNMS%20_%20A35%20Dorchester%20-%20Weymouth%20Road%20Roundabout%20Improvements%20Report%20_%20Final.pdf | A35 Weymouth Road Roundabout | 1 |  | 2011 | 2002 | 2.0383 | 1.4653 | construction cost, discounted | -28.11% | the "forecast over-estimated the cost. However, the forecast estimate would have been more accurate without the 15% optimism bias included in the predicted costs." | 15% |  |  |  |  | 2006-06-01 | 2008-04-01 | 2010-10-01 | 2011-03-31 | 5 | 48.322 | 39.745 | 21.9 | 28
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636097/Full_report.pdf | A38 Dobwalls Bypass | 5 | 2004 | 2008 | 2002 | 35.42 | 45.66 | investment cost, undiscounted | 28.91% | none |  | 2003-05-01 | [5 empty] | 2007-02-01 | 2009-03-01 | 25 | 67.6 | 43.63 | 2.48 | 1.11
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A41%20Aston%20Clinton%20Bypass/A41%20Aston%20Clinton%20BP%20POPE%20FYA%20-%20website%20version.pdf | A41 Aston Clinton Bypass | 5 |  | 2003 | 2002 | 38.5 | 44.1 | Present value costs, discounted | 14.55% | [8 empty] | 2001-08-01 | 2003-10-01 | 26 | 109.1 | 53.2 | 3 | 1.2
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636102/Full_report.pdf | A419 Blunsdon Bypass | 5 | 2006 | 2009 | 2002 | 51.5 | 55.7 | investment cost, undiscounted | 8.155% |  |  | 2002-04-01 | 2005-10-01 | 2006-03-01 |  |  |  | 2006-09-01 | 2009-03-01 | 30 | 73.3 | 159.7 | 2.1 | 2.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130943mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A419_Calcutt_Access_Roads_Report___Final.pdf | A419 Calcutt Access Roads |  | 2002 | 2003 | 1998 | 2.5339 | 2.0312 | Present value costs, discounted | -19.84% | none | ? | [7 empty] | 2003-08-01 |  | 2.412 | 3.729 | 1.05 | 1.84
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123506mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A419%20Commonhead%20Junction/POPE_A419_Commonhead_FYA_final.pdf | A419 Commonhead Junction | 5 |  | 2007 | 2002 | 15.2 | 14 | investment cost, undiscounted | -7.895% | none | ? | [6 empty] | 2005-09-01 | 2009-03-01 | 42 | 68.9 | 79.3 | 4.7 | 6.5
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782616/POPE_A421_Bedford_FYA_Report.pdf | A421 Bedford to M1 junction 13 |  | 2008 | 2010 | 2002 | 170.5 | 162.1 | investment cost, undiscounted | -4.927% |  |  | 2004-12-01 | 2008-02-01 |  |  |  |  | 2008-10-28 | 2010-12-01 | 26 | 1605.7 | 948.2 | 9.9 | 6.2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124731mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A421%20Great%20Barford%20Bypass/POPE_A421_Great_Barford_FYA_FINAL.pdf | A421 Great Barford Bypass |  | 2004 | 2006 | 2002 | 61.6 | 58.6 | investment cost, undiscounted | -4.87% | [8 empty] | 2005-09-01 | 2006-08-01 | 11 | 244.7 | 394.9 | 7.2 | 15.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123211mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A428%20Caxton%20Common%20to%20Hardwick%20Improvement/POPE___A428_Caxton_Common_to_Harwick_Improvement_FYA_final.pdf | A428 Caxton Common to Hardwick | 5 | 2004 | 2007 | 2002 | 41.7 | 48.6 | investment cost, undiscounted | 16.55% | HA procedures for scheme implementation including cost control measures have been significantly altered through the introduction of the Project Control Framework and three-point cost estimating | [7 empty] | 2005-08-01 | 2007-05-01 | 21 | 209.5 | 117.9 | 5.1 | 2.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A43%20Silverstone%20Bypass%20A43%20Whitfield%20Turn%20A43-M40-B4031/POPE%20_%20A43%20Silverstone%20FYA%20report%20_%20final.pdf | A43 Improvements (Silverstone) | 5 | 2000 | 2002 | 2002 | 59.5 | 115.6 | investment cost, undiscounted | 94.29% | "Reasons include delays in construction caused by the foot-and-mouth outbreak, poor winter weather, and additional work undertaken as part of preparation for the 2002 Formula One weekend" | [7 empty] | 2000-11-01 | 2002-09-01 | 22 | 317.8 | 163.3 | 4.2 | 1.4
https://nationalhighways.co.uk/media/04hovg0z/a43-abthorpe-roundabout-one-year-post-opening-evaluation.pdf | A45 Ryton-on Dunsmore Junction Improvement
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130959mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A45___A445_Ryton-on-Dunsmore_Junction_Improvement_Report___Final.pdf | A45 Ryton-on Dunsmore Junction Improvement |  |  | 2005 | 2002 | 3.0556 | 4.5206 | Present value costs, discounted | 47.94% | "The underestimate of costs is largely a result of construction costs being higher than expected" | [8 empty] | 2005-08-01 |  | 8.63 | 14.11 | 1.83 | 2.1
https://nationalhighways.co.uk/media/t2upwjfp/a45-a46-tollbar-one-year-post-opening-evaluation.pdf
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130221mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A45_Wilby_Way_Report___Final.pdf | A45/A509 Wilby Way Junction Segregated Left Turn Lane |  |  | 2008 | 2002 | 1.599 | 1.604 | Works, Land & Other PVC (discounted) | 0.3127% | [9 empty] | 2008-06-01 |  | 133.4 | 46.7 | 79.7 | 28.1
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782623/POPE_A453_Widening_OYA_Report.pdf | A453 Widening M1 J24 to A52 | 1 |  | 2015 | 2002 | 120.606 | 125.282 | investment cost, undiscounted | 3.877% | none | ? | [6 empty] | 2013-01-01 | 2015-07-01 | 30 | 238.9 | 249.2 | 2.42 | 2.47
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A46%20Newark%20-%20Lincoln%20Improvement/POPE%20_%20A46%20Newark%20Lincoln%205YA%20report%20_%20final.pdf | A46 Newark – Lincoln | 5 | 1992 | 2003 | 2002 | 38.567 | 40.623 | investment cost, undiscounted | 5.331% | [8 empty] | 2001-11-01 | 2003-07-01 | 20 | 196.4 | 281 | 3.9 | 6.9
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782604/POPE_A46_Newark_to_Widmerpool_FYA_Report.pdf | A46 Newark to Widmerpool Improvement | 5 | 2009 | 2012 | 2002 | 297.9 | 299.5 | investment cost, undiscounted | 0.5371% |  |  | 2005-07-01 | 2007-09-01 |  | 2009-01-01 |  |  | 2009-06-01 | 2012-04-01 | 34 | 998.28 | 723.66 | 4.3 | 3.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130151mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A46___A607_Hobby_Horse_Roundabout_Report___Final.pdf | A46/A607 Junction Improvement Scheme |  |  | 2006 | 2002 | 3.6055 | 3.126 | Total PVC (discounted) | -13.3% | none | 5.885% | [6 empty] | 2005-09-01 | 2006-05-01 | 8 | 15.6846 | 12.9434 | 4.4 | 4.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130647mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A47_Honingham_Roundabout_Report___Final.pdf | A47 Honingham Roundabout | 1 |  | 2009 | 2002 | 1.752 | 1.935 | Total PVC (discounted) | 10.45% | construction of the scheme taking place during severe inclement weather | [6 empty] | 2007-03-01 | 2008-10-01 | 2009-02-01 | 4 | 0.945 | -3.256 | 0.7 | -1.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123240mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A47%20Thorney%20Bypass/POPE_A47_Thorney_FYA_Final.pdf | A47 Thorney Bypass |  | 2002 | 2005 | 2002 | 19.2 | 25.4 | Scheme cost, discounted | 32.29% | none | [7 empty] | 2004-09-01 | 2005-12-01 | 15 | 39.8 | 47.3 | 2 | 1.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130811mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A47___A10_Hardwick_Roundabout_Report___Final.pdf | A47/A10 Hardwick Roundabout |  | 2002 | 2003 | 1998 | 3.5909 | 7.3927 | Present value costs, discounted | 105.9% | none | [8 empty] | 2003-10-01 |  | 66.256 | 48.816 | 18 | 6.6
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130355mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A5_Bayleys_Roundabout_Report___Final.pdf | A5 Bayleys Roundabout | 1 |  | 2008 | 2002 | 0.682 | 0.496 | Works, Land and Other PVC (not 60 year maintainance cost) | -27.27% | none | ? | [7 empty] | 2008-03-01 |  | 10.092 | 25.349 | 13 | 35.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130704mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A5_Dunstable_Queue_Relocation_-_Re-Evaluation_Report___Final.pdf | A5 Dunstable Queue Relocation Scheme | [6 empty] | no cost data | [10 empty] | 2004-03-01
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A5-Nesscliffe-Bypass/A5%20Nesscliffe%20BP%20POPE%20FYA%20-%20website%20version.pdf | A5 Nesscliffe Bypass |  | 1991 | 2003 | 2002 | 25.55 | 20.35 | Scheme cost, discounted | -20.35% | none | ? | [6 empty] | 2002-06-01 | 2003-03-01 |  | 72 | 67.19 | 2.8 | 3.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122936mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A5-Weeford-Fazeley-Improvement/POPE_A5_Weeford_Fazeley_FYA%20_FINAL.pdf | A5 Weeford - Fazeley Improvements |  | 2002 | 2005 | 2002 | 31.7 | 37.8 | investment cost, undiscounted | 19.24% | [8 empty] | 2004-04-01 | 2005-10-01 | 18 | 225.2 | 168 | 6.1 | 3.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A500%20Basford%20Hough%20Shavington%20Bypass/A500%20Basford%2C%20Shavington%20and%20Hough%20Bypass%20POPE%20FYA%20-%20website%20version.pdf | A500 Basford, Hough, Shavington Bypass | 5 | 2000 | 2003 | 2002 | 30.85 | 54.16 | Investment costs | 75.56% | none | [7 empty] | 2001-06-01 | 2003-05-01 |  | 51.07 | 96.51 | 1.63 | 1.76
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124823mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A500%20City%20Road%20%26%20Stoke%20Junction%20Improvement/POPE_A500_City_Rd_Stoke_Rd_FYA_final.pdf | A500 City Rd & Stoke Rd Junction improvements | 5 | 2002 | 2006 | 2002 | 36.3 | 64.1 | Investment costs | 76.58% | none | [7 empty] | 2004-02-01 | 2006-09-01 | 31 | 120.5 | 157.8 | 3.5 | 2.7
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636115/Full_report.pdf | A5117/ A550 Deeside Park Junctions Improvement | 5 | 2006 | 2009 | 2002 | 43.8 | 51.7 | investment cost, undiscounted | 18.04% | - Difficult weather conditions, particularly the exceptionally wet summer of 2007; - Problems associated with works by the Statutory Undertakers, namely a major gas main diversion and - Increased compensation events. |  | 2002-02-01 | 2005-10-01 | 2006-05-01 |  |  |  | 2006-10-01 | 2008-08-01 | 22 | 927.3 | 178.6 | 14.2 | 2.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130617mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A523_Leek_to_Hazel_Grove_Report___Final.pdf | A523 Leek to Hazel Grove Traffic Safety Measures |  |  | 2002 | 1994 | 0.62132 | 0.90989 | Present value costs, discounted | 46.44% | none | [7 empty] | 1998-01-01 | 2002-05-01 | 40 | 9.87 | 6.89 | 15.91 | 7.57
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130520mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A55___A483_Junction_Improvement_Segregated_Left-Turn_Lane_Report___Final.pdf | A55 / A483 Junction Improvement Scheme-Segregated Left Turn from A483(N) to A55 |  |  | 2003 | 1998 | 1.0951 | 0.93692 | Present value costs, discounted | -14.45% | none | ? | [6 empty] | 2003-05-01 | 2005-06-01 | 25 | 5.522 | 4.151 | 5.04 | 2.84
https://nationalhighways.co.uk/media/faih0do3/a556-knutsford-to-bowdon-pope-one-year-after-report.pdf | A590 High and Low Newton Bypass
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/448780/A590_High_to_Low_Newton_Bypass_FYA_Report_FINAL.pdf | A590 High and Low Newton Bypass | 5 |  | 2008 | 2002 | 30.1 | 32.1 | investment cost, undiscounted | 6.645% | [8 empty] | 2006-07-01 | 2008-04-01 | 21 | 95.4 | 91.8 | 3.7 | 2.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/a595-parton-lillyhall/a595-parton-lillyhall-final.pdf | A595 Parton to Lillyhall Improvement |  | 2007 | 2009 | 2002 | 34.7 | 35.6 | investment cost, undiscounted | 2.594% | [8 empty] | 2007-02-01 | 2009-03-01 | 25 | 52.3 | 105 | 2.2 | 4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130442mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A596___Calva_Brow_Junction_Improvement_Report___Final.pdf | A596 Calva Brow |  |  | 2003 | 1994 | 0.639 | 0.515 | Present value costs, discounted | -19.41% | none | ? | [7 empty] | 2003-03-01 |  | 1.38 | -0.121 | 2.15 | -0.24
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603131014mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A596_Northside_Junction_Improvement_Report___Final.pdf | A596 Northside |  |  | 2002 | 1994 | 0.791 | 0.93393 | Present value costs, discounted | 18.07% | [8 empty] | 1999-06-01 | 2002-09-01 |  | 3.65 | 4.693 | 4.6 | 5.02
https://nationalhighways.co.uk/media/hsdf42u4/a5-m1-dunstable-northern-bypass-1-year-after-pope-report.pdf | A6 Alvaston | [6 empty] | no cost data | [9 empty] | 2015-06-01 | 2017-05-01
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A6-Alvaston-Improvement/POPE%20_%20A6%20Alvason%205YA%20_%20website%20part%20B.pdf | A6 Alvaston | 5 |  | 2004 | 2002 | 15.1 | 21.7 | Scheme costs, undiscounted | 43.71% | The AST does not provide a breakdown of scheme costs into the different elements (e.g. land, civil engineering, etc) so the source of the cost increases cannot be identified | [8 empty] | 2003-12-01 |  | 54.8 | 230.7 | 3.6 | 10.5
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A6-Clapham-Bypass/POPE%20_%20A6%20Clapham%20FYA%20report%20_%20final.pdf | A6 Clapham Bypass |  | 1998 | 2002 | 2002 | 38.8 | 40.9 | Present value costs, discounted | 5.412% | [8 empty] | 2001-05-01 | 2002-12-01 | 20 | 61.3 | 53.4 | 1.6 | 1.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A6-Great-Glen-Bypass/POPE%20_%20A6%20Great%20Glen%20FYA%20report%20_%20final.pdf | A6 Great Glen Bypass |  |  | 2003 | 2002 | 21.513 | 21.172 | Scheme costs, discounted | -1.585% | [8 empty] | 2001-06-01 | 2003-02-01 |  | 62.7 | 38.5 | 2.2 | 1.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A6-Rothwell-Desborough-Bypass/POPE%20_%20A6%20Rothwell%20-%20Desborough%20FYA%20report%20_%20final.pdf | A6 Rothwell-Desborough Bypass | 5 | 2000 | 2003 | 2002 | 11.8 | 18.8 | Scheme costs, discounted | 59.32% | none | [7 empty] | 2001-05-01 | 2003-08-01 | 27 | 65.1 | 24.1 | 5.5 | 1.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A6-Rushden-and-Higham-Ferrers-Bypass/POPE%20_%20A6%20Rushden%20%26%20Higham%20Ferrers%20FYA%20report%20_%20final.pdf | A6 Rushden – Higham Ferrers Bypass | 5 | 2000 | 2003 | 2002 | 10.6 | 16.2 | Scheme costs, discounted | 52.83% | none. BCR is similar so maybe no motivation to investigate | [7 empty] | 2002-04-01 | 2003-08-01 | 28 | 27.8 | 39.7 | 2.6 | 2.4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130852mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A63_Garrison_Road_Roundabout_Report___Final.pdf | A63 Garrison Road Roundabout |  |  | 2008 | 2002 | 1.433 | 1.343 | Scheme costs, undiscounted | -6.281% | [8 empty] | 2008-09-01 | 2008-12-01 | 3 | 7.412 | 5.93 | 6.3 | 5.4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124001mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A63%20Melton%20Grade%20Separated%20Junction/POPE_A63_Melton_GSJ_FYA_FINAL.pdf | A63 Melton Grade Separated Junction | 5 |  | 2006 | 2002 | 14.1 | 39.2 | Scheme costs, discounted | 178% | "The cost overrun was notified to the Secretary of State and was subject to a Highways Agency internal audit and an external review. The review found that the cost increase consists of a combination of design changes and scope increases; external factors (such as weather impacts, and archaeological finds); contractor cost increases; and other items such as land and other additional costs" | [7 empty] | 2004-09-01 | 2006-10-01 | 25 | 115.1 | 58.2 | 7.3 | 1.4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A63%20Selby%20Bypass/A63%20Selby%20BP%20POPE%20FYA%20-%20website%20version.pdf | A63 Selby Bypass | 5 | 1997 | 2004 | 2002 | 45.67 | 65.92 | Scheme costs, undiscounted | 44.34% | "problems with the bypass swing bridge (which delayed the opening of the scheme) may have partly contributed to this increase in costs." | [7 empty] | 2001-07-01 | 2004-06-01 | 35 | 374.1 | 167.45 | 6.8 | 2.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122931mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A64%20Colton%20Lane%20GSJ/POPE_A64_Colton_Lane_5YA_final.pdf | A64 Colton Lane Grade Separated Junction | 5 | 2003 | 2005 | 2002 | 10.94 | 11.98 | Scheme costs, undiscounted | 9.506% | [8 empty] | 2004-01-01 | 2005-06-01 | 17 | 14.5 | 43.7 | 1.4 | 3.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130321mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/A64%20Hopgrove%20Roundabouts.pdf | A64 Hopgrove Roundabouts | 1 | 2008 | 2009 | 2002 | 9.54 | 7.11 | Total Project PVC | -25.47% | "lack of risk allowance or optimism bias in the outturn costs" | 12.9% | [6 empty] | 2008-12-01 | 2009-10-01 | 10 | 82.92 | 26.77 | 7.1 | 3.5
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130340mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A64___Top_Lane_Copmanthorpe_Junction_Improvement_Report___Final.pdf | A64 Top Lane Copmanthorpe | [6 empty] | no cost data |  |  |  | 1997-03-01 | 1999-06-01 | 1999-12-01 |  |  |  |  | 2002-10-01 |  | 53.56 | 101.89 | 21.4 | 40.76
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A650%20Bingley%20Relief%20Road/POPE%20_%20A650%20Bingley%20FYA%20_%20website%20part%20C.pdf | A650 Bingley Relief Road | 5 |  | 2003 | 2002 | 104.2 | 92.3 | Present value costs, discounted | -11.42% | works cost lower, but land cost higher | ? | [6 empty] | 2001-07-01 | 2003-12-01 | 29 | 267.4 | 221.9 | 2.5 | 2.4
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124907mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A66%20Carkin%20Moor%20to%20Scotch%20Corner%20Improvement/pope___A66_Carkin_Moor_to_Scotch_Corner_FYA___report___Final.pdf | A66 Carkin Moor to Scotch Corner Improvement | 5 |  | 2007 | 2002 | 8.7 | 12 | Present value costs, discounted | 37.93% | none | [7 empty] | 2006-07-01 | 2007-09-01 | 14 | 41.1 | 20.2 | 4.7 | 1.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124835mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A66%20Greta%20Bridge%20to%20Stephen%20Bank%20Improvement/A66_Greta_Bridge_FYA_Report_POPE_Final.pdf | A66 Greta Bridge to Stephen Bank Improvement | 5 |  | 2007 | 2002 | 5.1 | 11 | Investment cost | 115.7% | none | [7 empty] | 2006-07-01 | 2007-09-01 | 14 | 34.3 | 26.3 | 5.6 | 2.3
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/442347/POPE___A66_Long_Newton_Junction_5YA___Final.pdf | A66 Long Newton Grade Separated Junction | 5 | 2005 | 2008 | 2002 | 9.81 | 10.32 | investment cost, undiscounted | 5.199% |  |  |  | 2003-07-01 |  | 2005-02-01 |  |  | 2007-06-01 | 2008-06-01 | 12 | 21.88 | 10.96 | 2.08 | 1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130328mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___A66_Sadberge_GSJ_Report___Final.pdf | A66 Sadberge Grade Separated Junction |  | 2001 | 2002 | 1994 | 0.60936 | 0.44008 | Present value costs, discounted | -27.78% | none | ? | [7 empty] | 2002 |  | 2.156 | 3.171 | 3.54 | 7.21
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A66%20Stainburn%20%26%20Great%20Clifton%20Bypass/POPE%20_%20A66%20Stainburn%205YA%20report%20_%20final.pdf | A66 Stainburn and Great Clifton Bypass | 5 | 2003 | 2002 | 2002 | 9.56 | 12.73 | Present value costs, discounted | 33.16% | "the majority of the increase [60%] in outturn cost [£3.175m] appears to come from land costs [£1.891m] as the predicted land costs are less than 25% of the outturn costs" | [7 empty] | 2001-06-01 | 2002-12-01 | 18 | 56.7 | 42.4 | 5.9 | 3.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123403mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/A66%20Temple%20Sowerby%20Bypass%20%26%20Imp%20at%20Winderwath/A66_Temple_Sowerby_FYA_Report_Final.pdf | A66 Temple Sowerby Bypass & Improvements at Winderwath | 5 | 2005 | 2007 | 2002 | 31.9 | 32.3 | Investment cost | 1.254% | [8 empty] | 2006-02-01 | 2007-10-01 | 20 | 67.8 | 51.2 | 2.5 | 1.8
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636105/Full_report.pdf | A69 Haydon Bridge Bypass | 5 | 2005 | 2009 | 2002 | 24.9 | 32.5 | investment cost, undiscounted | 30.52% | "increase in construction costs was caused by earthworks taking longer than expected due to inclement weather" | ? | 2003-12-01 | 2006-04-01 | 2006-09-01 |  |  |  | 2007-01-01 | 2009-03-25 | 26 | 45.5 | 38.2 | 2.5 | 1.2
https://nationalhighways.co.uk/media/yb4d53ab/pope-m1-j10-to-j13-five-year-evaluation.pdf | M1 J10 to 13 smart motorway and junction improvements | 5 | 2006 | 2012 | 2010 | 462 | 345 | investment cost, undiscounted. 5YA study lacked detail | -25.32% | lower construction costs | ? | [6 empty] | 2009-12-01 | 2012-12-01 | 36 | 510 | -242 | 1.4 | -0.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130429mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M1_J25_Safety_Improvements_Report___Final.pdf | M1 J25 Safety Improvements |  |  | 2005 | 2002 | 1.453 | 1.754 | total project costs | 20.72% | none | [8 empty] | 2004-09-01 |  | 4.979 | 4.292 | 3.1 | 2.8
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782634/POPE_M1_J25-28_FYA_Report.pdf | M1 J25 to 28 Widening | 5 |  | 2010 | 2002 | 296.9 | 261.7 | investment cost, undiscounted | -11.86% | "outturn scheme costs are lower than the forecast estimate ... due to the redesign of the scheme that took place once the contractor, was appointed. The scheme was redesigned using a Compact Motorway Design with a variable width verge which removed or reduced in scale a number of scheme elements. For instance the scheme originally included four new bridges over the motorway but after the redesign process this was reduced to one." | ? |  | 2006-06-01 |  |  |  |  | 2007-10-01 | 2010-05-01 | 31 | 561.3 | 449.3 | 1.9 | 1.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130305mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M1_J28_Capacity_Improvement_Scheme_Report___Final.pdf | M1 J28 Capacity Improvement Scheme |  |  | 2006 | 2002 | 2.977 | 3.282 | Total Project Costs, undiscounted | 10.25% | [8 empty] | 2005-10-01 | 2006-03-01 | 5 | 3.1 | 4.962 | 0.96 | 1.59
https://nationalhighways.co.uk/media/v50o2fqt/m1-j28-35a-pope-one-year-after.pdf | M1 J31-32 | 1 | [5 empty] | cost out of scope | [9 empty] | 2013-09-01 | 2017-03-01 | 32
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M1%20J31%20to%20J32%20Widening/POPE%20_%20M1%20J31-32%20OYA%20_%20website%20part%20B.pdf | M1 J31-32 | 1 | 2009 | 2008 | 2002 | 17.1 | 11.3 | Present value costs, discounted | -33.92% | none | ? | [6 empty] | 2007-01-01 | 2008-02-01 | 13 | 296.8 | 39.7 | 9.6 | 3.5
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130228mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE%20LNMS%20_%20M1%20J34%20North%20Roundabout%20Signalisation%20Report%20_%20Final.pdf | M1 J34 North | 1 | 2009 | 2011 | 2002 | 1.726 | 1.023 | construction cost | -40.73% | Inaccurate forecast | 3% | [6 empty] | 2011-01-01 | 2011-03-01 | 2 | 50.223 | 53.717 | 29.1 | 52.5
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872103/M1_J39_J42_POPE_OYA_with_foreword_FINAL_Jan_2020.pdf | M1 J39 to 42 smart motorway |  | 2010 | 2016 | 2010 | 113.7 | 114.9 | investment cost, undiscounted | 1.055% | [8 empty] | 2013-11-01 | 2016-01-01 | 26 | 305 | 309.2 | 2.1 | 2.1
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636120/Full_report.pdf | M1 J6a to 10 Widening | 5 | 2006 | 2008 | 2002 | 275.7 | 249.6 | investment cost, undiscounted | -9.467% | none | ? | [6 empty] | 2006-03-01 | 2008-12-01 | 33 | 2033.7 | 1196.5 | 7.1 | 4.6
https://nationalhighways.co.uk/media/v00b2zum/m1-j45-one-year-post-opening-evaluation.pdf | M11 J4 Northbound Slip Road Merge
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130408mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M11_J4_Northbound_Slip_Road_Merge_Report___Final.pdf | M11 J4 Northbound Slip Road Merge |  | 1998 | 2003 | 1998 | 1.206 | 1.0955 | Present value costs, discounted | -9.161% | [9 empty] | 2003-12-01 |  | 15.903 | 11.91 | 11.77 | 10.87
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130913mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M20_M26_Street_Lighting_Report___Final.pdf | M20/M26 Street Lighting |  |  | 2008 | 2002 | 1.844 | 1.469 | Scheme costs, discounted | -20.34% | none | ? | [7 empty] | 2007-02-01 |  | 1.755 | 10.591 | 0.56 | 3.96
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M25%20J12-15%20Widening/POPE%20_%20M25%20J12-15%20FYA%20report%20_%20final%20web%20version.pdf | M25 J12 - J15 Widening |  | 1996 | 2005 | 2002 | 110.5 | 127.2 | Scheme costs, undiscounted | 15.11% | [8 empty] | 2004-01-01 | 2005-12-01 | 23 | 735.9 | 702.3 | 5.8 | 4.8
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/387327/POPE___M25_J16-23_OYA___Final.pdf | M25 J16-12 Widening |  |  | 2012 | 2002 | 476.1 | 421.8 | Investment Costs, undiscounted | -11.41% | none | ? | [6 empty] | 2009-05-01 | 2012-05-01 | 36 | 1565 | 2336.1 | 3.4 | 5.7
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130711mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M25_J16-17_Climbing_Lane_Report___Final.pdf | M25 J16-17 Climbing Lane |  |  | 2001 | 1994 | 0.737 | 2.421 | Scheme costs, discounted | 228.5% | none | [8 empty] | 2001-05-01 |  | 15.802 | 15.802 | 20.1 | 6.5
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130846mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M25_J18-19_Climbing_Lane_Report___Final.pdf | M25 J18-19 Climbing Lane |  |  |  | 1994 | [13 empty] | 2000-12-01 |  |  |  | 16.59
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636112/Full_report.pdf | M25 J1b – 3 (& controlled motorway) |  |  | 2007 | 2002 | 65.5 | 52.9 |  | -19.24% | none | ? | [9 empty] | 241.1 | 32.6 | 2.1 | 0.5
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872134/M25_J23_J27_POPE_OYA_with_foreword_FINAL_Jan_2020.pdf | M25 J23-27 Smart Motorway All Lane Running | 1 | 2012 | 2014 | 2002 | 149.7 | 121.2 | investment cost, undiscounted | -19.04% | Value engineering | ? | [6 empty] | 2013-02-01 | 2014-11-01 | 21 | 306.1 | 222.6 | 2.1 | 1.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130422mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M25_J27-28_Climbing_Lane_Report___Final.pdf | M25 J27-28 Climbing Lane Study (Site 4) |  |  | 2001 | 1994 | 1.997 | 1.786 | discounted | -10.57% | none | ? | [7 empty] | 2001-09-01 |  | 10.07 | 10.07 | 5.04 | 5.64
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/448746/POPE_M25_J27-30_OYA_Final.pdf | M25 J27-30 Widening (Section 4 - M11 to A13) | 1 | 2007 | 2012 | 2002 | 419.7 | 300.2 | investment cost, undiscounted | -28.47% | none | ? | [7 empty] | 2012-12-01 |  | 686.7 | 341.8 | 2.1 | 1.4
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/387301/POPE___M25_J28_Brook_Street_Five_Year_After_Study___Final.pdf | M25 J28 (A12 Brook Street) Improvements | 5 | 2006 | 2008 | 2002 | 10.47 | 11.09 | investment cost, undiscounted | 5.922% |  |  | 2006-11-01 |  | 2007-04-01 |  |  |  | 2007-05-01 | 2008-03-01 | 10 | 264.3 | 44.4 | 17.9 | 2.8
https://nationalhighways.co.uk/media/ezmp00ee/m25-junction-30-a13-corridor-congestion-relieving-project-1-year-post-opening-project-evaluation-pope.pdf | M25 J5 to 7 smart motorway | [6 empty] | no cost data | [9 empty] | 2015-02-01 | 2017-03-01 | 25
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872132/M25_J5_J7_POPE_OYA_with_foreword_FINAL_Jan_2020.pdf | M25 J5 to 7 smart motorway |  | 2012 | 2014 | 2010 | 124.4 | 102.8 | investment cost, undiscounted | -17.36% | Value engineering | ? | [6 empty] | 2013-10-01 | 2014-04-01 | 6 | 388.9 | 417.6 | 2.5 | 3.1
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/387293/POPE___M27_J11-12_FYA___Final.pdf | M27 J11-12 Climbing Lanes | 5 | 2007 | 2008 | 2002 | 13.3 | 13.2 | investment cost, undiscounted | -0.7519% |  |  |  | 2006-10-01 | 2007-02-01 | 2007-02-01 |  |  | 2008-01-01 | 2008-09-01 | 8 | 53.1 | 48.5 | 5.5 | 4.1
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636124/Full_report.pdf | M27 J3-4 Widening | 5 | 2006 | 2009 | 2002 | 29.9 | 27.4 | investment cost, undiscounted | -8.361% | "forecast costs included more gantries than actually installed, and an additional element of lighting that was not implemented" | ? |  | 2007-02-01 |  |  |  |  | 2008-02-01 | 2009-01-01 | 11 | 355.8 | 99.4 | 12 | 3.6
https://nationalhighways.co.uk/media/uz5bnzsf/m3-junctions-2-to-4a-all-lane-running-one-year-post-opening-project-evaluation.pdf | M4 J18 Eastbound Diverge | 1 | [5 empty] | no cost data | [9 empty] | 2014-05-01 | 2017-08-01 | 39
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M4%20Junction%2018%20Eastbound%20Diverge/pope-m4-j18-fya-report-final.pdf | M4 J18 Eastbound Diverge |  | 2002 | 2005 | 2002 | 11 | 9.9 | scheme cost | -10% | none | ? | [6 empty] | 2005-02-01 | 2005-11-01 | 9 | 55.4 | 10 | 3.5 | 1.4
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872109/M4_M5_POPE_OYA_with_foreword_FINAL_Jan_2020.pdf | M4 J19 to 20 & M5 J15 to 17 smart motorway |  | 2010 | 2014 | 2002 | 56.5 | 63.2 | investment cost, undiscounted | 11.86% | none | ? | [6 empty] | 2012-01-01 | 2014-01-01 | 24 |  |  |  | N/A
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130559mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M4___M5_Almondsbury_Interchange_Phase_2A_Report___Final.pdf | M4/M5 Almondsbury Interchange Phase 2A M5 Southbound & Northbound to M4 Eastbound |  | 2003 | 2004 | 1998 | 2.6051 | 2.104 | Present Value Cost (PVC), discounted | -19.23% | none | ? | [7 empty] | 2004-03-01 |  | 6.97 | 2.26 | 2.67 | 1.07
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/782573/POPE_M40_J15_Longbridge_FYA_Report.pdf | M40 J15 (Longbridge) Bypass | 5 | 2006 | 2010 | 2002 | 58.9 | 61.7 | investment cost, undiscounted | 4.754% |  |  | 2006-07-01 | 2007-03-01 |  |  |  |  | 2008-03-01 | 2010-06-01 | 27 | 268.9 | 126.6 | 5.1 | 2.1
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603123106mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M40A404%20Handy%20Cross%20Junction%20Improvement/POPE_M40_Handy_Cross_5YA_FINAL.pdf | M40 J4 / A404 Handy Cross Junction Improvements | 5 |  | 2007 | 2002 | 14.8 | 14.8 | Investment Cost (PVC) , discuounted | 0% | [8 empty] | 2005-10-01 | 2012-05-01 | 79 | 55.9 | 55.7 | 3.8 | 3.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124943mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M5%20Climbing%20lanes/POPE_M5_Climbing_Lanes_5YA_Study_Final.pdf | M5 Climbing Lanes Five Years After Study - HALLEN HILL |  |  | 2005 | 2002 | 7.1 | 6.7 | Scheme cost | -5.634% | [8 empty] | 2005-10-01 | 2006-06-01 | 8 | 24.2 | 13 | 2.9 | 2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124943mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M5%20Climbing%20lanes/POPE_M5_Climbing_Lanes_5YA_Study_Final.pdf | M5 Climbing Lanes Five Years After Study - Naish Hill |  |  | 2005 | 2002 | 10.3 | 11.4 |  | 10.68% | [11 empty] | 75.4 | 45.5 | 6.6 | 3.9
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603124943mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M5%20Climbing%20lanes/POPE_M5_Climbing_Lanes_5YA_Study_Final.pdf | M5 Climbing Lanes Five Years After Study - Twickenham Hill |  |  | 2005 | 2002 | 12.4 | 12.5 |  | 0.8065% | [11 empty] | 55.8 | 32.1 | 5.3 | 2.5
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130919mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/M5%20Junction%2012%20Improvements.pdf | M5 J12 Improvements | 1 |  | 2011 | 2002 | 2.517 | 1.452 | Scheme cost | -42.31% | The outturn cost is substantially lower than predicted. This is due to a number of differences between the outturn cost and appraised cost. Key contributors to this difference include: - Works costs approximately £0.5m higher than predicted; - ‘Other’ costs (Statutory undertakers , design, site preparation and consultants fees) approximately £0.87m less than anticipated; - Site supervision approximately £40,000 less than anticipated; and - There is no risk allowance or optimism bias in outturn costs (this had accounted for approximately £178,958 in the predicted costs). | 7.11% | [6 empty] | 2010-09-06 | 2011-01-01 | 4 | 625 | 30.181 | 248.4 | 20.8
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130451mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M5_J31_Lane_Drop_Report___Final.pdf | M5 J31 – Main Line Lane Drop at Parallel Diverge (Capacity Improvement) |  | 2002 | 2003 | 2002 | 1.7428 | 1.6256 | Present Value Cost (PVC), discounted | -6.722% | none | ? | [7 empty] | 2003-03-01 |  | 8.8883 | 9.1447 | 5.1 | 5.63
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636127/Full_report.pdf | M6 Carlisle to Guards Mill Improvement | 5 | 2005 | 2008 | 2002 | 125.8 | 103.5 | investment cost, undiscounted | -17.73% | none | ? | 2002-06-01 | 2005-09-01 |  |  |  |  | 2006-07-01 | 2008-12-01 | 29 | 86.6 | 96.9 | 3 | 3.6
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872130/M6_J10a_J13_POPE_OYA_with_foreword_FINAL_Jan_2020.pdf | M6 J10a to 13 smart motorway |  | 2013 | 2016 | 2010 | 96.8 | 91.3 | investment cost, undiscounted | -5.682% | [8 empty] | 2013-10-01 | 2016-02-01 | 28
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130246mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M6_J32_SB_Widening_Report___Final.pdf | M6 J32 Southbound Widening |  |  | 2009 | 2002 | 3.95 | 4.015 | Present Value Cost (PVC), discounted | 1.646% | [8 empty] | 2009-01-01 | 2009-06-12 | 6 | 206.2 | 113.28 | 64.7 | 28.2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130551mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M6_J40_Improvements_Report___Final.pdf | M6 J40 Modification |  | 2003 | 2005 | 2002 | 2.0629 | 2.481 | Total Project Cost, undiscounted | 20.27% | none | [7 empty] | 2005-09-01 | 2005-12-01 | 3 | 260.57 | 100.45 | 60.91 | 44.6
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872126/M6_J5_J8_POPE_OYA_with_foreword_FINAL_Jan_2020.pdf | M6 J5 to 8 smart motorway |  | 2011 | 2014 | 2002 | 102.926 | 85.226 | investment cost, undiscounted | -17.2% | none | ? | [6 empty] | 2012-01-01 | 2014-04-01 | 27 | 356.9 | -332.9 |  | N/A
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/872128/M6_J8_J10a_POPE_FYA_with_foreword_FINAL_Jan_2020.pdf | M6 J8 to 10a smart motorway | 5 | 2007 | 2011 | 2002 | 116 | 117.3 | investment cost, undiscounted | 1.121% | [8 empty] | 2012-01-01 | 2011-03-01 | 19 | 383.7 | 155.2 | 3.8 | 1.3
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603122103mp_/http://assets.highways.gov.uk/our-road-network/pope/major-schemes/M60%20J5-8%20Widening/POPE%20_%20M60%20J5-8%20OYA%20_%20Website%20part%20C.pdf | M60 J5-8 | 1 | 2000 | 2006 | 1994 | 83.7 | 86.1 | Scheme Costs, discounted | 2.867% |  |  |  | 1995-06-01 |  |  |  |  | 2003-01-01 | 2006-06-22 | 42 | 255 | 190 | 3 | 2.2
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130745mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M62_J10_Westbound_Diverge_Report___Final.pdf | M62 J25-30 Smart Motorway |  | 2002 |  | 2002 | [12 empty] | 2006-02-01 | 2006-04-01 | 2 | 28.3 | 2.8 | 17.7 | 1.81
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603130525mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M62_J25_Eastbound_Entry_Slip_Report___Final.pdf | M62 J27 Westbound Entry | 1 | [16 empty] | 2002-03-01 |  | 2.6127 | 1.1295 | 3.57 | 1.54
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/515795/POPE___M62_J25-30_SM_OYA_Final_Report.pdf | M62 J25-30 Smart Motorway | 1 | 2011 | 2013 | 2002 | 116.2 | 95.9 | investment cost, undiscounted | -17.47% | Value engineering | ? | [6 empty] | 2011-11-01 | 2013-10-01 | 23 |  |  |  | N/A
https://webarchive.nationalarchives.gov.uk/ukgwa/20140603131030mp_/http://assets.highways.gov.uk/our-road-network/pope/lnms/POPE_LNMS___M62_J27_Westbound_Entry_Slip_Report___Final.pdf | M62 J27 Westbound Entry |  | 2001 | 2002 | 1994 | 1.1583 | 0.56794 | Present Value Cost (PVC), discounted | -50.97% | none | ? | [6 empty] | 2001-10-01 | 2002-05-01 | 7 | 5.26 | 2.643 | 4.451 | 4.65
https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/636138/Full_report.pdf | M62 J6 Improvement | 5 |  | 2008 | 2002 | 31.1 | 31.3 | investment cost, undiscounted | 0.6431% |  |  | 2003-06-01 | 2006-10-01 | 2007-01-01 |  |  |  | 2007-04-01 | 2008-12-01 | 20 | 72 | 92.8 | 2.34 | 2.91
[21 empty] | 27512.9488 | 19853.8403
Note on AA2: Indirect tax as benefit
Note on E3: 2016
Note on S4: Local Network Management Economy Scheme Identification Study
Note on X21: £21.4m in 1988 prices
Note on Y21: £214.5m in 2002 prices
Note on L26: Risk allowance of 9% (£104,511) as well as optimism uplift of 3% (£36,535)
Note on X34: £38.8m
Note on AA34: 1.9
Note on E40: 2017
Note on E64: 2017
Note on L69: Risk allowance = £491,369 (18%) Optimism uplift = £163,311 (6%)
Note on E74: 2004
Note on E82: 2017
Note on E87: 2017
Note on B94: Given poor performance, project was subject to an internal audit and external review by NAO. Change programme intoduced to strengthen ability to manage budgets
Note on L97: Risk Allowance + optimism uplift = £1.09m
Note on E98: 2002
Note on G107: Appendix 4, pg52 Investment cost
Note on E111: 2017
Note on E116: 2018
Note on E122: 2000
Note on G122: £1.134m
Note on H122: not available
Note on X122: £18.808m
Note on E128: 2017
Note on E132: 2017
Note on X134: £559.2m
Note on Y134: n/a
Note on AA134: 7.5
Note on L141: risk allowance / optimism bias of approximately £178,958 included in the predicted costs
Note on X144: £237.6m
Note on AA147: 6.4
Note on E150: 2006
Note on G150: £1.6m
Note on H150: not available
Note on E151: 2002
Note on H151: not available
Note on X152: £729.1m
Note on Y152: n/a
Note on AA152: 4.9